## Software Dev Plan
SOFTWARE DEVELOPMENT PROJECT PLAN
BURNDOWN
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK POC | AMOUNT OF WORK IN HOURS |  |  | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9
|  |  | ESTIMATE | COMPLETED | REMAINING |  |  |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Thu | Wed | Thu | Fri | Sat | Sun | Mon | Thu | Wed | Thu | Fri | Sat | Sun | Mon | Thu | Wed | Thu | Fri | Sat | Sun
1 | Problem Identification |  | 14 | 14 | 0 |  |  |  | 100%
1.1 | Gathering Project Ideas | Sharv, Pawan | 7 | 7 | 0 | 2024-02-26 | 2024-03-01 | 5 | 100% | bar: WEEK 1 Mon to WEEK 1 Fri; WEEK 8 Mon to WEEK 8 Thu
1.1.1 | Project desc Doc | Bishesh | 1 | 1 | 0 | 2024-02-28 | 2024-03-01 | 3 | 100% | bar: WEEK 1 Wed to WEEK 1 Fri; WEEK 8 Mon to WEEK 8 Thu
1.2 | PPT making for review | Sharv | 2 | 2 | 0 | 2024-02-28 | 2024-03-03 | 5 | 100% | bar: WEEK 1 Wed to WEEK 1 Sun; WEEK 8 Mon to WEEK 8 Thu
1.3 | Discussing Guidelines+ Scope | All | 3 | 3 | 0 | 2024-03-04 | 2024-03-04 | 1 | 100% | bar: WEEK 2 Mon to WEEK 2 Wed; WEEK 8 Mon to WEEK 8 Thu
1.4 | Task and POC allocation | Pawan | 1 | 1 | 0 | 2024-03-05 | 2024-03-05 | 1 | 100% | bar: WEEK 2 Thu; WEEK 8 Mon to WEEK 8 Thu
2 | Requirement Elecitation + Design | All | 32 | 32 | 0 |  |  |  | 100%
2.1 | Class Diagram | Sharv | 6 | 6 | 0 | 2024-03-14 | 2024-03-14 | 1 | 100% | bar: WEEK 3 Thu; WEEK 8 Mon to WEEK 8 Thu
2.2 | Activity Diagram | Pawan | 6 | 6 | 0 | 2024-03-15 | 2024-03-15 | 1 | 100% | bar: WEEK 3 Fri; WEEK 8 Mon to WEEK 8 Thu
2.3 | Use-Case Diagram | Sharv | 6 | 6 | 0 | 2024-03-15 | 2024-03-16 | 2 | 100% | bar: WEEK 3 Fri to WEEK 3 Sat; WEEK 8 Mon to WEEK 8 Thu
2.4 | Data-Flow Diagram | Sharv + Bishesh | 6 | 6 | 0 | 2024-03-18 | 2024-03-18 | 1 | 100% | bar: WEEK 4 Mon; WEEK 8 Mon to WEEK 8 Thu
2.5 | UI Design | Pawan+Vedant+Sharv | 8 | 8 | 0 | 2024-03-19 | 2024-03-29 | 11 | 100% | bar: WEEK 4 Tue to WEEK 5 Fri; WEEK 8 Mon to WEEK 8 Thu
3 | Coding |  | 99 | 99 | 0 |  |  |  | 100%
3.1 | Fluentify System Design | Sharv | 8 | 8 | 0 | 2024-04-09 | 2024-04-10 | 2 | 100% | bar: WEEK 7 Thu to WEEK 7 Wed; WEEK 8 Mon to WEEK 8 Thu
3.2 | Login System Design | Pawan | 8 | 8 | 0 | 2024-04-09 | 2024-04-11 | 3 | 100% | bar: WEEK 7 Thu to WEEK 7 Thu; WEEK 8 Mon to WEEK 8 Thu
3.3 | Course Reg System Design | Vedant | 8 | 8 | 0 | 2024-04-10 | 2024-04-12 | 3 | 100% | bar: WEEK 7 Wed to WEEK 7 Fri; WEEK 8 Mon to WEEK 8 Thu
3.4 | Marks System Design | Bishesh + Vedant | 8 | 8 | 0 | 2024-04-11 | 2024-04-12 | 2 | 100% | bar: WEEK 7 Thu to WEEK 7 Fri; WEEK 8 Mon to WEEK 8 Thu
3.5 | Quiz System Design | Sharv+Pawan | 12 | 12 | 0 | 2024-04-15 | 2024-04-16 | 2 | 100% | bar: WEEK 8 Mon to WEEK 8 Thu
3.6 | Flashcard System Design | Pawan | 10 | 10 | 0 | 2024-04-15 | 2024-04-16 | 2 | 100% | bar: WEEK 8 Mon to WEEK 8 Thu
3.7 | Setting up GitHub Repository | Pawan | 2 | 2 | 0 | 2024-04-08 | 2024-04-08 | 1 | 100% | bar: WEEK 7 Mon; WEEK 8 Mon to WEEK 8 Thu
3.8 | Frontend | Vedant+Bishesh | 20 | 20 | 0 | 2024-04-11 | 2024-04-22 | 12 | 100% | bar: WEEK 7 Thu to WEEK 9 Mon
3.9 | Backend + DB integration | Pawan + Sharv | 20 | 20 | 0 | 2024-04-15 | 2024-04-23 | 9 | 100% | bar: WEEK 8 Mon to WEEK 9 Thu
3.10 | Debugging | All | 3 | 3 | 0 | 2024-04-24 | 2024-04-24 | 1 | 100% | bar: WEEK 8 Mon to WEEK 8 Thu; WEEK 9 Wed
4 | Testing + Manual + Software Conclusions |  | 5 | 5 | 0 |  |  |  | 100%
4.1 | Conclusion + Scope | All | 1 | 1 | 0 | 2024-04-24 | 2024-04-24 | 1 | 100% | bar: WEEK 8 Mon to WEEK 8 Thu; WEEK 9 Wed
4.2 | Docs | All | 3 | 3 | 0 | 2024-04-23 | 2024-04-24 | 2 | 100% | bar: WEEK 8 Mon to WEEK 8 Thu; WEEK 9 Thu to WEEK 9 Wed
4.3 | Testing | All | 5 | 5 | 0 | 2024-04-24 | 2024-04-27 | 4 | 100% | bar: WEEK 8 Mon to WEEK 8 Thu; WEEK 9 Wed to WEEK 9 Sat
|  |  | ESTIMATE | COMPLETED | REMAINING | EST/ DAYS
BURNDOWN DATA |  | TOTAL HOURS | 150 | 150 | 0 | 2.381

## Dropdown Keys
Dropdown Keys - DO NOT DELETE
STATUS KEY | PRIORITY KEY
Complete | High
Overdue | Medium
In Progress | Low
Not Started